## FTK
Site ID | Governate | RFTI | Delivery | Installation | Status of Integration | Integration date | TDD | Subcon
8104 | Babil | 2025-03-20 | 2025-03-21 | 2025-03-22 | Integrated | 2025-03-23 |  | TAC
7496 | Qaddissiya | 2025-04-20 | 2025-04-22 | 2025-04-23 | Integrated | 2025-04-25 |  | TAC
7300 | Qaddissiya | 2025-04-20 | 2025-04-22 | 2025-04-23 | Integrated | 2025-04-23 | TDD, C2 or C3 | MFC
6577 | Basra | 2025-04-20 | 2025-04-21 | 2025-04-22 | Integrated | 2025-04-23 | TDD, C2 or C3 | MFC
7460 | Thiqar | 2025-04-17 | 2025-04-18 | 2025-04-20 | Integrated | 2025-04-24 | TDD, C2 or C3 | KCT
7358 | Thiqar | 2025-04-10 | 2025-04-12 | 2025-04-13 | Integrated | 2025-04-20 |  | KCT
6995 | Basra | 2025-04-17 | 2025-04-18 | 2025-04-19 | Integrated | 2025-04-20 | TDD, C2 or C3 | MFC
6994 | Basra | 2025-04-10 | 2025-04-12 | 2025-04-13 | Integrated | 2025-04-20 | TDD, C1 | KCT
6580 | Basra | 2025-04-17 | 2025-04-21 | 2025-04-21 | Integrated | 2025-04-25 | TDD, C1 | MFC
6999 | Basra | 2025-04-17 | 2025-04-21 | 2025-04-21 | Integrated | 2025-04-25 | TDD, C2 or C3 | MFC
7130 | Basra | 2025-04-17 | 2025-04-21 | 2025-04-21 | Integrated | 2025-04-25 | TDD, C2 or C3 | MFC
7291 | Qaddissiya | 2025-04-14 | 2025-04-17 | 2025-04-18 | Integrated | 2025-04-21 | TDD, C2 or C3 | MFC
7468 | Thiqar | 2025-04-17 | 2025-04-21 | 2025-04-21 | Integrated | 2025-05-26 | TDD, C2 or C3 | KCT
6591 | Basra | 2025-04-17 | 2025-04-21 | 2025-04-22 | Integrated | 2025-04-24 | TDD, C1 | KCT
6573 | Basra | 2025-04-17 | 2025-04-21 | 2025-04-22 | Integrated | 2025-04-25 | TDD, C2 or C3 | KCT
8126 | Basra | 2025-04-10 | 2025-04-12 | 2025-04-13 | Integrated | 2025-04-19 | TDD, C2 or C3 | KCT
8364 | Basra | 2025-04-14 | 2025-04-16 | 2025-04-17 | Integrated | 2025-04-19 | TDD, C2 or C3 | MFC
8120 | Babil | 2025-05-19 | 2025-05-19 | 2025-05-19 | Integrated | 2025-05-19 |  | TAC
8129 | Babil | 2025-05-21 | 2025-05-21 | 2025-05-21 | Integrated | 2025-05-02 | TDD, C1 | TAC
7281 | Qaddissiya | 2025-04-22 | 2025-04-22 | 2025-04-23 | Integrated | 2025-04-25 | TDD, C2 or C3 | TAC
7277 | Qaddissiya | 2025-04-22 | 2025-04-22 | 2025-04-23 | Integrated | 2025-04-24 | TDD, C1 | MFC
6558 | Basra | 2025-04-22 | 2025-04-23 | 2025-04-24 | Integrated | 2025-04-26 | Yes | MFC
7183 | Basra | 2025-04-14 | 2025-04-16 | 2025-04-16 | Integrated | 2025-04-16 | planned | MFC
7456 | Thiqar | 24/4 | 2025-04-24 | 2025-04-26 | Integrated | 2025-04-28 | TDD, C1 | KCT
7487 | Thiqar | 24/4 | 2025-04-24 | 2025-04-25 | Integrated | 2025-05-01 | planned | KCT
7479 | Thiqar | 24/4 | 2025-04-24 | 2025-04-25 | Integrated | 2025-05-01 | TDD, C1 | KCT
7474 | Thiqar | 24/4 | 2025-04-24 | 2025-04-25 | Integrated | 2025-04-30 |  | KCT
8123 | Babil | 2025-04-24 | 2025-04-24 | 2025-04-24 | Integrated | 2025-04-27 | TDD, C2 or C3 | TAC
7302 | Qaddissiya | 2025-04-24 | 2025-04-25 | 2025-04-25 | Integrated | 2025-04-27 | Yes | MFC
7282 | Qaddissiya | 2025-04-24 | 2025-04-25 | 2025-04-26 | Integrated | 2025-04-26 | TDD, C1 | MFC
6993 | Basra | 24/4 | 2025-04-24 | 2025-04-25 | Integrated | 2025-04-28 | TDD, C1 | MFC
6997 | Basra | 24/4 | 2025-04-24 | 2025-04-25 | Integrated | 2025-04-27 | planned | MFC
7279 | Qaddissiya | 2025-04-28 | 2025-04-29 | 2025-04-30 | Integrated | 2025-05-06 | TDD, C1 | MFC
4851 | Missan | 2025-04-27 | 2025-04-30 | 2025-05-01 | Integrated | 2025-05-08 | TDD, C1 | SPTECH
7238 | Missan | 2025-04-27 | 2025-04-30 | 2025-05-01 | Integrated | 2025-05-08 | TDD, C1 | MFC
7234 | Missan | 2025-04-27 | 2025-04-30 | 2025-05-02 | Integrated | 2025-05-08 | TDD, C1 | MFC
7288 | Qaddissiya | 2025-04-27 | 2025-04-29 | 2025-04-30 | Integrated | 2025-05-07 | TDD, C1 | MFC
7242 | Missan | 2025-04-27 | 2025-04-30 | 2025-05-01 | Integrated | 2025-05-06 | TDD, C2 or C3 | MFC
8134 | Babil | 2025-04-27 | 2025-05-01 | 2025-05-01 | Integrated | 2025-05-08 | TDD, C1 | TAC
7318 | Thiqar | 2025-04-27 | 2025-04-30 | 2025-05-01 | Integrated | 2025-05-08 | TDD, C1 | KCT
7478 | Thiqar | 2025-04-27 | 2025-04-30 | 2025-05-01 | Integrated | 2025-07-09 | TDD, C1 | KCT
7455 | Thiqar | 1930-04-01 | 2025-04-30 | 2025-05-02 | Integrated | 2025-05-06 | TDD, C2 or C3 | KCT
8374 | Basra | 2025-05-28 | 2025-05-28 | 2025-05-28 | Integrated | 2025-06-03 | TDD, C1 | KCT
6569 | Basra | 2025-06-15 | 2025-06-16 | 2025-06-16 | Integrated | 2025-06-22 | TDD, C2 or C3 | MFC
6570 | Basra | 2025-05-23 | 2025-05-25 | 2025-05-25 | Integrated | 2025-06-01 | TDD, C1 | MFC
6571 | Basra | 2025-05-20 | 2025-05-20 | 2025-05-21 | Integrated | 2025-05-28 | TDD, C1 | KCT
8138 | Basra | 2025-05-18 | 2025-05-18 | 2025-05-18 | Integrated | 2025-05-21 | TDD, C2 or C3 | IPT
8100 | Basra | 2025-05-19 | 2025-05-20 | 2025-05-21 | Integrated | 2025-05-28 | TDD, C1 | IPT
6996 | Basra | 2025-05-05 | 2025-05-05 | 2025-05-05 | Integrated | 2025-05-08 | TDD, C2 or C3 | IPT
6588 | Basra | 2025-05-05 | 2025-05-05 | 2025-05-05 | Integrated | 2025-05-08 | TDD, C2 or C3 | MFC
8112 | Babil | 2025-05-04 | 2025-05-05 | 2025-05-05 | Integrated | 2025-05-12 | TDD, C1 | TAC
7295 | Qaddissiya | 2025-05-04 | 2025-05-05 | 2025-05-06 | Integrated | 2025-05-07 | TDD, C1 | MFC
7235 | Missan | 2025-05-12 | 2025-05-12 | 2025-05-12 | Integrated | 2025-05-17 | TDD, C2 or C3 | SPTECH
7240 | Missan | 2025-05-12 | 2025-05-12 | 2025-05-12 | Integrated | 2025-05-16 | TDD, C1 | MFC
7239 | Missan | 2025-05-29 | 2025-05-29 | 2025-05-29 | Integrated | 2025-06-10 | TDD, C1 | SPTECH
7253 | Missan | 2025-06-01 | 2025-09-01 | 2025-09-01 | Integrated | 2025-06-02 | TDD, C1 | MFC
7121 | Basra | 2025-06-05 | 2025-06-05 | 2025-06-06 | Integrated | 2025-06-22 | TDD, C1 | IPT
6584 | Basra | 2025-08-30 | 2025-08-30 | 2025-08-31 | Integrated | 2025-09-03 | TDD, C2 or C3 | MRC
7208 | Basra | 2025-05-09 | 2025-05-08 | 2025-05-09 | Integrated | 2025-05-13 | TDD, C2 or C3 | KCT
6585 | Basra | 2025-05-15 | 2025-05-15 | 2025-05-17 | Integrated | 2025-05-20 | TDD, C2 or C3 | KCT
6557 | Basra | 2025-05-17 | 2025-05-14 | 2025-05-17 | Integrated | 2025-05-20 | TDD, C1 | MFC
6574 | Basra | 2025-05-21 | 2025-05-20 | 2025-05-21 | Integrated | 2025-05-24 | TDD, C1 | MFC
6587 | Basra | 2025-05-11 | 2025-05-12 | 2025-05-12 | Integrated | 2025-05-13 | planned | MFC
8121 | Babil | 2025-05-10 | 2025-05-08 | 2025-05-10 | Integrated | 2025-05-10 | TDD, C1 | TAC
8107 | Babil | 2025-05-10 | 2025-05-10 | 2025-07-03 | Integrated | 2025-07-06 | Yes | MFC
7278 | Qaddissiya | 2025-06-20 | 2025-06-20 | 2025-06-20 | Integrated | 2025-06-21 | TDD, C1 | MFC
8096 | Babil | 2025-06-11 | 2025-06-11 | 2025-06-11 | Integrated | 2025-06-11 | TDD, C2 or C3 | TAC
8106 | Basra | 2025-05-20 | 2025-05-20 | 2025-05-21 | Integrated | 2025-05-25 | planned | IPT
7473 | Thiqar | 2025-05-15 | 2025-05-15 | 2025-05-16 | Integrated | 2025-05-21 | TDD, C1 | KCT
7492 | Thiqar | 2025-05-17 | 2025-05-18 | 2025-05-18 | Integrated | 2025-05-24 | TDD, C2 or C3 | KCT
7119 | Basra | 2025-06-16 | 2025-06-15 | 2025-06-16 | Integrated | 2025-06-21 |  | MFC
6491 | Basra | 2025-05-06 | 2025-05-06 | 2025-05-07 | Integrated | 2025-05-11 | planned | TAC
6583 | Basra | 2025-05-12 | 2025-05-13 | 2025-05-14 | Integrated | 2025-05-15 | TDD, C1 | KCT
6582 | Basra | 2025-05-17 | 2025-05-18 | 2025-05-18 | Integrated | 2025-05-20 | TDD, C2 or C3 | IPT
7140 | Basra | 2025-05-22 | 2025-05-22 | 2025-05-22 | Integrated | 2025-06-06 | planned | MFC
7489 | Thiqar | 2025-05-22 | 2025-05-22 | 2025-05-23 | Integrated | 2025-06-01 | TDD, C1 | KCT
7485 | Thiqar | 2025-05-21 | 2025-05-20 | 2025-05-21 | Integrated | 2025-05-22 | TDD, C2 or C3 | KCT
7466 | Thiqar | 2025-08-10 | 2025-08-11 | 2025-08-11 | Integrated | 2025-08-17 | TDD, C2 or C3 | KCT
6575 | Basra | 2025-06-01 | 2025-06-01 | 2025-06-01 | Integrated | 2025-06-11 | TDD, C2 or C3 | MFC
6535 | Basra | 2025-05-25 | 2025-05-25 | 2025-05-25 | Integrated | 2025-06-03 | TDD, C2 or C3 | IPT
8348 | Missan | 2025-06-06 | 2025-06-06 | 2025-06-06 | Integrated | 2025-06-21 | TDD, C1 | SPTECH
7139 | Basra | 2025-05-18 | 2025-05-19 | 2025-05-19 | Integrated | 2025-05-29 | TDD, C1 | MFC
6599 | Basra | 2025-05-20 | 2025-05-20 | 2025-05-20 | Integrated | 2025-05-28 | TDD, C2 or C3 | IPT
7482 | Thiqar | 2025-05-22 | 2025-05-22 | 2025-05-23 | Integrated | 2025-05-27 | planned | KCT
7241 | Missan | 2025-06-06 | 2025-06-06 | 2025-06-06 | Integrated | 2025-06-22 | TDD, C2 or C3 | SPTECH
7246 | Missan | 2025-05-15 | 2025-05-15 | 2025-05-16 | Integrated | 2025-05-23 | TDD, C2 or C3 | SPTECH
8000 | Basra | 2025-06-05 | 2025-06-05 | 2025-06-05 | Integrated | 2025-06-22 |  | MFC
6589 | Basra | 2025-06-16 | 2025-06-15 | 2025-06-17 | Integrated | 2025-06-21 | planned | IPT
7486 | Thiqar | 2025-05-27 | 2025-05-27 | 2025-05-27 | Integrated | 2025-06-11 |  | KCT
8114 | Babil | done | 2026-01-21 | 2026-01-21 | Integrated | 2026-01-21 |  | horizon
2961 | Muthanna | 2025-05-20 | 2025-05-21 | 2025-05-22 | Integrated | 2025-05-24 | TDD, C1 | MFC
7269 | Muthanna | 2025-07-10 | 2025-06-01 | 2025-07-10 | Integrated | 2025-07-10 | TDD, C1 | MFC
8097 | Babil | 2025-05-29 | 2025-05-28 | 2025-06-02 | Integrated | 2025-06-02 | TDD, C2 or C3 | TAC
8108 | Babil | 2025-06-11 | 2025-06-11 | 2025-06-11 | Integrated | 2025-06-11 | TDD, C1 | TAC
8818 | Basra | 2025-06-02 | 2025-06-02 | 2025-06-04 | Integrated | 2025-06-06 | planned | TAC
4468 | Basra | 2026-05-01 | 2026-05-01 | 2026-05-01 | Integrated | 2025-10-08 | planned | TAC
7135 | Basra | 2025-03-28 | 2025-03-29 | 2025-03-29 | Integrated | 2025-04-10 | Yes | MFC
7199 | Basra | 2025-04-10 | 2025-04-10 | 2025-04-11 | Integrated | 2025-04-15 | planned | KCT
7475 | Thiqar | 2025-04-13 | 2025-04-14 | 2025-04-14 | Integrated | 2025-04-15 | TDD, C1 | KCT
534 | Basra | 2026-01-01 | 2026-01-01 |  |  |  |  | Oraxel
6531 | Basra | 2025-05-31 | 2025-05-31 | 2025-05-31 | Integrated | 2025-06-02 | TDD, C2 or C3 | MFC
8593 | Basra | 2025-06-01 | 2025-06-01 | 2025-06-02 | Integrated | 2025-06-06 | TDD, C1 | IPT
8130 | Basra | 2025-06-01 | 2025-06-01 | 2025-06-01 | Integrated | 2025-06-06 |  | MFC
7296 | Qaddissiya | 2025-06-12 | 2025-06-13 | 2025-06-13 | Integrated | 2025-06-15 | TDD, C2 or C3 | MFC
7299 | Qaddissiya | 2025-06-12 | 2025-06-12 | 2025-06-12 | Integrated | 2025-06-14 | planned | MFC
8116 | Babil | 2025-07-03 | 2025-07-01 | 2025-07-01 | Integrated | 2025-07-03 | TDD, C1 | TAC
7495 | Qaddissiya | 2025-06-14 | 2025-06-14 | 2025-06-14 | Integrated | 2025-06-25 | Yes | MFC
8136 | Babil | done | done | done | Integrated | 2025-10-02 | TDD, C2 or C3 | TAC
8142 | Babil | 2025-07-20 | 2025-07-21 | 2025-07-21 | Integrated | 2025-07-26 | TDD, C2 or C3 | TAC
8137 | Babil | 2025-07-26 | 2025-07-23 | 2025-07-23 | Integrated | 2025-07-30 | TDD, C2 or C3 | TAC
8135 | Babil | done | 2025-08-25 | 2025-08-25 | Integrated | 2025-08-26 | TDD, C2 or C3 | TAC
8446 | Babil | 2025-07-26 | 2025-07-23 | 2025-07-23 | Integrated | 2025-07-30 | TDD, C2 or C3 | TAC
7268 | Muthanna | 2025-07-25 | 2025-07-25 | 2025-07-25 | Integrated | 2025-07-30 | TDD, C2 or C3 | MFC
7270 | Muthanna | 2025-08-20 | 2025-08-21 | 2025-08-21 | Integrated | 2025-08-22 | TDD, C2 or C3 | MFC
7273 | Muthanna | 2025-07-25 | 2025-07-25 | 2025-07-25 | Integrated | 2025-07-30 | TDD, C2 or C3 | MFC
7272 | Muthanna | 2025-07-25 | 2025-07-25 | 2025-07-25 | Integrated | 2025-07-29 | TDD, C2 or C3 | MFC
7262 | Muthanna | 2025-07-22 | 2025-07-22 | 2025-07-23 | Integrated | 2025-07-23 | TDD, C2 or C3 | MFC
7280 | Qaddissiya | 2025-06-22 | 2025-06-23 | 2025-06-24 | Integrated | 2025-06-24 | TDD, C1 | MFC
7293 | Qaddissiya | 2025-06-11 | 2025-06-15 | 2025-06-14 | Integrated | 2025-06-21 | planned | MFC
7301 | Qaddissiya | 2025-10-24 | 2025-10-24 | 2025-10-24 | Integrated | 2025-10-30 | Yes | MFC
7285 | Qaddissiya | 2025-06-20 | 2025-06-20 | 2025-06-20 | Integrated | 2025-06-24 | TDD, C1 | MFC
7237 | Missan | 2025-06-19 | 2025-06-19 | 2025-06-19 | Integrated | 2025-06-22 | TDD, C1 | SPTECH
7236 | Missan | 2025-06-05 | 2025-06-05 | 2025-06-06 | Integrated | 2025-06-06 |  | SPTECH
7344 | Thiqar | 2025-07-02 | 2025-07-03 | 2025-07-03 | Integrated | 2025-07-09 | TDD, C1 | KCT
7465 | Thiqar | 2025-06-22 | 2025-06-25 | 2025-06-25 | Integrated | 2025-06-25 | TDD, C1 | KCT
7481 | Thiqar | 2025-06-22 | 2025-06-22 | 2025-06-22 | Integrated | 2025-06-25 |  | KCT
7006 | Basra | 2025-06-25 | 2025-06-26 | 2025-06-27 | Integrated | 2025-07-01 | TDD, C2 or C3 | MFC
7469 | Thiqar | 2025-06-16 | 2025-06-16 | 2025-06-17 | Integrated | 2025-06-23 | TDD, C1 | KCT
7206 | Basra | 2016-07-01 | 2016-07-01 | 2025-07-01 | Integrated | 2025-07-21 | TDD, C2 or C3 | MFC
7254 | Missan | 2025-06-25 | 2025-06-26 | 2025-06-28 | Integrated | 2025-07-17 |  | MFC
6593 | Basra | 2025-07-21 | 2025-07-23 | 2025-07-23 | Integrated | 2025-07-24 | TDD, C2 or C3 | MFC
7315 | Thiqar | 2025-07-02 | 2025-07-03 | 2025-07-04 | Integrated | 2025-07-08 | TDD, C2 or C3 | IPT
6590 | Basra | 2025-07-02 | 2025-07-02 | 2025-07-03 | Integrated | 2025-07-08 | TDD, C2 or C3 | MFC
7245 | Missan | 2025-07-01 | 2025-07-02 | 2025-07-04 | Integrated | 2025-07-17 | TDD, C1 | MFC
6592 | Basra | 2025-07-16 | 2025-07-16 | 2025-07-01 | Integrated | 2025-07-22 | TDD, C2 or C3 | MFC
7138 | Basra | 2025-07-02 | 2025-07-03 | 2025-07-03 | Integrated | 2025-07-09 | TDD, C2 or C3 | TAC
4591 | Basra | 2025-08-03 | 2025-08-04 | 2025-08-05 | Integrated | 2025-08-07 | planned | TAC
7480 | Thiqar | 2025-07-17 | 2025-07-17 | 2025-07-19 | Integrated | 2025-07-24 | TDD, C2 or C3 | IPT
7248 | Missan | 2025-06-25 | 2025-06-26 | 2025-06-27 | Integrated | 2025-07-09 | TDD, C2 or C3 | MFC
7250 | Missan | 2025-07-26 | 2025-07-28 | 2025-07-29 | Integrated | 2025-08-03 | TDD, C2 or C3 | SPTECH
7122 | Basra | 2025-07-28 | 2025-07-28 | 2025-07-28 | Integrated | 2025-08-04 | TDD, C2 or C3 | MFC
4776 | Missan | 2025-07-01 | 2025-07-02 | 2025-07-02 | Integrated | 2025-07-17 | TDD, C1 | SPTECH
6563 | Basra | 2025-06-19 | 2025-06-21 | 2025-06-21 | Integrated | 2025-06-24 | TDD, C1 | TAC
6578 | Basra | 2025-08-20 | 2025-08-20 | 2025-08-21 | Integrated | 2025-08-24 |  | MFC
7488 | Thiqar | 2025-07-21 | 2025-07-23 | 2025-07-24 | Integrated | 2025-07-31 | TDD, C2 or C3 | IPT
7305 | Qaddissiya | 2025-07-01 | 2025-07-02 | 2025-07-02 | Integrated | 2025-07-03 | TDD, C1 | MFC
7292 | Qaddissiya | 2025-07-01 | 2025-07-02 | 2025-07-08 | Integrated | 2025-07-28 | planned | MFC
8131 | Babil | 2025-07-07 | 2025-07-08 | 2025-07-08 | Integrated | 2025-07-27 | TDD, C2 or C3 | TAC
7290 | Qaddissiya | 2025-07-03 | 2025-07-07 | 2025-07-13 | Integrated | 2025-07-17 | TDD, C1 | MFC
7483 | Thiqar | 2025-07-14 | 2025-07-14 | 2025-07-15 | Integrated | 2025-07-20 | TDD, C1 | IPT
7467 | Thiqar | 2025-07-14 | 2025-07-14 | 2025-07-15 | Integrated | 2025-07-20 |  | KCT
7136 | Basra | 2025-07-20 | 2025-07-21 | 2025-07-22 | Integrated | 2025-07-30 | TDD, C2 or C3 | MFC
7477 | Thiqar | 2025-07-17 | 2025-07-17 | 2025-07-19 | Integrated | 2025-07-20 | TDD, C2 or C3 | KCT
6595 | Basra | 2025-07-21 | 2025-07-23 | 2025-07-24 | Integrated | 2025-07-29 | planned | TAC
6998 | Basra | 2025-07-21 | 2025-07-22 | 2025-07-25 | Integrated | 2025-07-27 | planned | IPT
8808 | Basra | 2025-07-21 | 2025-07-23 | 2025-07-25 | Integrated | 2025-07-27 | TDD, C2 or C3 | MFC
7484 | Thiqar | 2025-07-21 | 2025-07-23 | 2025-07-23 | Integrated | 2025-07-30 | TDD, C2 or C3 | KCT
7249 | Missan | 2025-08-10 | 2025-08-10 | 2025-08-10 | Integrated | 2025-08-17 | TDD, C2 or C3 | SPTECH
7251 | Missan | 2025-07-26 | 2025-07-27 | 2025-07-31 | Integrated | 2025-08-05 | TDD, C2 or C3 | SPTECH
8806 | Basra | 2025-07-23 | 2025-07-24 | 2025-07-25 | Integrated | 2025-07-30 | TDD, C2 or C3 | MFC
8810 | Basra | 2025-07-23 | 2025-07-24 | 2025-07-24 | Integrated | 2025-08-03 | planned | KCT
8802 | Basra | 2025-07-22 | 2025-07-23 | 2025-07-24 | Integrated | 2025-07-30 | planned | TAC
7313 | Thiqar | 2025-07-26 | 2025-07-27 | 2025-07-28 | Integrated | 2025-07-30 | TDD, C2 or C3 | KCT
7211 | Basra | 2025-07-26 | 2025-07-27 | 2025-07-28 | Integrated | 2025-07-30 | planned | MFC
7265 | Muthanna | 2025-07-22 | 2025-07-22 | 2025-07-23 | Integrated | 2025-07-25 | planned | MFC
8132 | Babil | 2025-08-20 | 2025-08-21 | 2025-08-21 | Integrated | 2025-08-21 | TDD, C2 or C3 | MFC
8141 | Qaddissiya | 2025-08-19 | 2025-08-18 | 2025-08-20 | Integrated | 2025-08-25 | Yes | MFC
8113 | Babil | 2025-07-30 | 2025-07-30 | 2025-07-30 | Integrated | 2025-08-04 | TDD, C2 or C3 | TAC
7271 | Muthanna | 2025-08-27 | 2025-08-27 | 2025-08-27 | Integrated | 2025-08-30 | TDD, C2 or C3 | MFC
8143 | Babil | done | 2025-09-13 | 2025-09-14 | Integrated | 2025-09-16 | TDD, C2 or C3 | TAC
7286 | Qaddissiya | 2025-08-02 | 2025-08-02 | 2025-08-02 | Integrated | 2025-08-04 | Yes | MFC
7308 | Qaddissiya | 2025-08-20 | 2025-08-21 | 2025-08-25 | Integrated | 2025-08-26 | Yes | TAC
7267 | Muthanna | 2025-12-30 | 2025-12-31 | 2026-01-22 | Integrated | 2026-01-25 |  | MFC
7348 | Thiqar | 2025-07-31 | 2025-07-31 | 2025-08-01 | Integrated | 2025-08-05 | TDD, C2 or C3 | IPT
7100 | Babil | 2025-08-04 | 2025-08-05 | 2025-08-05 | Integrated | 2025-08-07 | TDD, C2 or C3 | TAC
8119 | Babil | 2025-08-05 | 2025-08-05 | 2025-08-06 | Integrated | 2025-08-12 | planned | TAC
7260 | Muthanna | 2025-08-28 | 2025-08-28 | 2025-08-29 | Integrated | 2025-08-30 | TDD, C2 or C3 | MRC
7264 | Muthanna | 2025-12-06 | 2025-12-06 | 2025-12-06 | Integrated | 2025-12-07 |  | MFC
2946 | Muthanna | 2025-08-29 | 2025-08-29 | 2025-08-30 | Integrated | 2025-08-30 | TDD, C2 or C3 | MFC
7297 | Qaddissiya | 2025-08-27 | 2025-08-27 | 2025-08-27 | Integrated | 2025-08-29 | Yes | TAC
8758 | Babil | ready | 2025-09-15 | 2025-09-15 | Integrated | 2025-09-16 | TDD, C2 or C3 | TAC
7493 | Thiqar | 2025-08-03 | 2025-08-03 | 2025-08-05 | Integrated | 2025-08-05 | TDD, C2 or C3 | KCT
8122 | Basra | 2025-09-06 | 2025-09-07 | 2025-09-07 | Integrated | 2025-09-08 | TDD, C2 or C3 | MRC
7462 | Thiqar | 2025-08-04 | 2025-08-05 | 2025-08-06 | Integrated | 2025-08-07 | TDD, C2 or C3 | IPT
4666 | Thiqar | 2025-08-27 | 2025-08-29 | 2025-08-30 | Integrated | 2025-09-05 | TDD, C2 or C3 | KCT
7454 | Thiqar | 2025-08-04 | 2025-08-05 | 2025-08-06 | Integrated | 2025-08-08 | TDD, C2 or C3 | KCT
7225 | Basra | 2025-08-04 | 2025-08-05 | 2025-08-05 | Integrated | 2025-08-19 | TDD, C2 or C3 | MFC
6579 | Basra | 2025-08-19 | 2025-08-19 | 2025-08-19 | Integrated | 2025-08-24 | TDD, C2 or C3 | MFC
7354 | Thiqar | 2025-08-26 | 2025-08-27 | 2025-08-27 | Integrated | 2025-09-05 | planned | KCT
7361 | Thiqar | 2025-08-27 | 2025-08-28 | 2025-08-30 | Integrated | 2025-09-05 |  | KCT
7360 | Thiqar | 2025-08-22 | 2025-08-25 | 2025-08-26 | Integrated | 2025-09-05 | planned | IPT
985 | Thiqar | 2025-08-22 | 2025-08-25 | 2026-03-01 | Integrated | 2026-03-01 |  | IPT
8684 | Basra | 2025-08-26 | 2025-08-26 | 2025-08-27 | Integrated | 2025-09-05 | TDD, C2 or C3 | KCT
8670 | Basra | 2025-08-22 | 2025-08-23 | 2025-08-23 | Integrated | 2025-09-05 | TDD, C2 or C3 | MFC
8680 | Basra | 2025-08-10 | 2025-08-11 | 2025-08-12 | Integrated | 2025-08-20 | TDD, C2 or C3 | KCT
7247 | Missan | 2025-08-27 | 2025-08-30 | 2025-08-30 | Integrated | 2025-09-05 | TDD, C2 or C3 | SPTECH
8671 | Basra | 2025-08-10 | 2025-08-11 | 2025-08-12 | Integrated | 2025-09-05 | planned | TAC
7252 | Missan | 2025-08-30 | 2025-08-30 | 2025-08-31 | Integrated | 2025-09-05 | TDD, C2 or C3 | SPTECH
7217 | Basra | 2025-08-27 | 2025-08-28 | 2025-08-28 | Integrated | 2025-09-05 | TDD, C2 or C3 | Oraxel
8807 | Basra | 2025-09-15 | done | 2025-09-16 | Integrated | 2025-09-16 | TDD, C2 or C3 | MFC
8832 | Basra | 2025-10-06 | done | done | Integrated | 2025-10-23 |  | MFC
8685 | Basra | 2025-08-30 | 2025-08-30 | 2025-08-31 | Integrated | 2025-09-03 | TDD, C2 or C3 | MRC
8687 | Thiqar | 2025-09-04 | 2025-09-05 | 2025-09-06 | Integrated | 2025-09-09 | TDD, C2 or C3 | KCT
8681 | Thiqar | 2025-08-28 | 2025-08-29 | 2025-08-30 | Integrated | 2025-09-05 | TDD, C2 or C3 | IPT
8682 | Basra | 2025-08-27 | 2025-08-27 | 2025-08-28 | Integrated | 2025-09-05 | planned | TAC
8686 | Basra | 2025-08-27 | 2025-08-28 | 2025-08-28 | Integrated | 2025-09-05 | TDD, C2 or C3 | MFC
8690 | Thiqar | 2025-09-04 | done | 2025-09-05 | Integrated | 2025-09-19 | TDD, C2 or C3 | MRC
7804 | Thiqar | 2025-09-09 | 2025-09-09 | 2025-09-10 | Integrated | 2025-09-22 | TDD, C2 or C3 | KCT
6369 | Qaddissiya | ready | 2025-09-15 | 2025-09-16 | Integrated | 2025-11-26 | yes | TAC
7566 | Babil | ready | 2025-09-17 | 2025-09-18 | Integrated | 2025-09-19 | TDD, C2 or C3 | MFC
8747 | Babil | ready | 2025-09-18 | 2025-09-18 | Integrated | 2025-09-20 | TDD, C2 or C3 | TAC
8587 | Babil | ready | 2025-09-17 | 2025-09-18 | Integrated | 2025-09-25 | TDD, C2 or C3 | MFC
6555 | Qaddissiya | ready | 2025-09-20 | 2025-09-20 | Integrated | 2025-09-27 |  | MFC
7841 | Basra | 2025-09-15 | 2025-09-15 | 2025-09-15 | Integrated | 2025-09-17 |  | MFC
8252 | Basra | 2025-09-15 | done | done | Integrated | done | planned | MRC
8109 | Basra | 2025-09-15 | 2025-09-16 | 2025-09-16 | Integrated | 2025-09-19 | planned | IPT
7207 | Basra | 2025-09-15 | done | done | Integrated | done |  | KCT
8161 | Qaddissiya |  | 2025-09-17 | 2025-09-17 | Integrated | 2025-09-18 | Yes | MFC
8163 | Qaddissiya | ready | 2025-09-17 | 2025-09-18 | Integrated | 2025-09-18 | TDD, C2 or C3 | MRC
8160 | Qaddissiya | ready | 2025-09-17 | 2025-09-18 | Integrated | 2025-09-22 | TDD, C2 or C3 | MRC
8658 | Babil | ready | 2025-09-18 | 2025-09-18 | Integrated | 2025-09-24 | planned | TAC
8596 | Babil |  | 2025-09-20 | 2025-09-23 | Integrated | 2025-09-24 | Yes | TAC
8244 | Basra | 2025-09-15 | done | 2025-09-17 | Integrated | 2025-09-22 | TDD, C2 or C3 | MFC
7797 | Basra | 2025-09-17 | 2025-09-17 | 2025-09-17 | Integrated | 2025-09-22 | TDD, C2 or C3 | MRC
8254 | Basra | 2025-09-15 | done | done | Integrated | done |  | IPT
8748 | Babil | ready | 2025-09-19 | 2025-09-20 | Integrated | 2025-09-25 | planned | TAC
7967 | Thiqar | 2025-09-21 | done | done | Integrated | done |  | IPT
7840 | Basra | 2025-09-21 | done | done | Integrated | done |  | MRC
8247 | Basra | 2025-09-21 | done | done | Integrated | done |  | MRC
8230 | Basra | 2025-09-21 | done | done | Integrated | done |  | IPT
7972 | Thiqar | 2025-09-21 | done | done | Integrated | done |  | KCT
8754 | Babil | ready | 2025-09-24 | 2025-09-25 | Integrated | 2025-09-25 |  | MFC
8246 | Basra | 2025-09-17 | done | done | Integrated | done | planned | KCT
8250 | Basra | 2025-09-17 | done | done | Integrated | done |  | KCT
8257 | Basra | 2025-09-17 | done | done | Integrated | done |  | MFC
7835 | Basra | 2025-09-17 | done | done | Integrated | done |  | IPT
8255 | Basra | 2025-09-17 | done | done | Integrated | done |  | Oraxel
8233 | Basra | 2025-09-17 | done | done | Integrated | done |  | MFC
8265 | Basra | 2025-09-17 | done | done | Integrated | done |  | MRC
8243 | Basra | 2025-09-22 | done | done | Integrated | 2025-10-23 |  | MFC
8237 | Basra | 2025-09-22 | done | done | Integrated | 2025-10-11 |  | IPT
7839 | Basra | 2025-09-25 | done | done | Integrated | done |  | TAC
7965 | Thiqar | 2025-09-22 | 2025-09-22 | 2025-09-22 | Integrated | done |  | KCT
7966 | Thiqar | 2025-09-22 | 2025-09-22 | 2025-09-22 | Integrated | done |  | KCT
7798 | Basra | 2025-09-25 | done | done | Integrated | done | installed | TAC
8741 | Babil | ready | 2025-09-26 | 2025-09-27 | Integrated | 2025-09-28 |  | TAC
8166 | Qaddissiya | ready | 2025-09-26 |  |  |  |  | MFC
8167 | Qaddissiya |  | 2025-09-26 | 2025-09-27 | Integrated | 2025-09-28 | Yes | MRC
8169 | Qaddissiya |  | 2025-09-26 | 2025-09-27 | Integrated | 2025-09-28 | Yes | MRC
8261 | Basra | 2025-09-25 | done | done | Integrated | 2025-10-20 | installed | TAC
8251 | Basra | done | done | done | Integrated | done | installed | MFC
8824 | Muthanna | 2025-10-05 | done | 2025-10-14 | Integrated | 2025-10-14 |  | MFC
7210 | Basra | 2025-10-05 | 2025-10-05 | 2025-10-06 | Integrated | 2025-10-10 |  | MFC
8263 | Basra | 2025-10-05 | done | done | Integrated | done |  | MFC
7975 | Thiqar | 2025-10-05 | done | done | Integrated | 2025-10-19 |  | IPT
8270 | Basra | 2025-10-05 | done | done | Integrated | 2025-10-19 |  | MRC
7973 | Thiqar | 2025-10-05 | done | done | Integrated | done |  | KCT
8229 | Basra | 2025-10-05 | 2026-04-01 | 2026-04-01 | Integrated | 2025-10-17 |  | IPT
7494 | Qaddissiya | done | 2025-10-05 | 2025-10-05 | Integrated | 2025-10-10 | done | MRC
8742 | Babil | Done | 2025-10-09 | 2025-10-09 | Integrated | 2025-10-15 |  | TAC
8295 | Muthanna | done | 2025-10-15 | 2025-10-16 | Integrated | 2025-10-26 |  | MFC
8597 | Babil |  | 2025-10-04 | 2025-10-04 | Integrated | 2025-10-11 |  | TAC
8743 | Babil | Done | 2025-10-06 | 2025-10-06 | Integrated | 2025-10-15 |  | TAC
8588 | Babil | done | 2025-10-08 | 2025-10-09 | Integrated | 2025-10-21 |  | TAC
8165 | Qaddissiya |  | 2025-10-08 | 2025-10-08 | Integrated | 2025-10-18 | installed | MFC
8736 | Babil | done | 2025-11-03 | 2025-11-03 | Integrated | 2025-11-03 |  | MRC
6598 | Basra | 2025-10-05 | done | done | Integrated | 2025-10-17 | TDD, C2 or C3 | TAC
7970 | Thiqar | 2025-10-05 | done | done | Integrated | 2025-10-23 | installed | KCT
7971 | Thiqar | 2025-10-06 | done | done | Integrated | 2025-10-23 | installed | KCT
8260 | Basra | 2025-10-07 | done | done | Integrated | 2025-10-23 |  | IPT
8595 | Babil | done | 2025-10-09 | 2025-10-10 | Integrated | 2025-10-15 |  | TAC
8753 | Babil | done | 2025-10-09 | 2025-10-10 | Integrated | 2025-10-15 |  | TAC
8750 | Babil | done | 2025-10-10 | 2025-10-10 | Integrated | 2025-10-18 |  | TAC
8299 | Muthanna | 2025-12-29 | 2025-12-29 | 2025-12-30 | Integrated | 2025-12-31 |  | MFC
8232 | Basra | done | done | done | Integrated | 2025-10-23 |  | MRC
916 | Basra | 2026-05-01 | 2026-05-01 | 2026-05-01 | Integrated | 2025-10-21 | planned | Oraxel
974 | Basra | 2026-05-01 | 2026-05-01 | 2026-05-01 | Integrated | 2026-02-13 |  | IPT
7723 | Missan | done | done | done | Integrated | 2025-10-25 |  | MRC
8240 | Basra | [6 empty] | IPT
8231 | Basra | done | done | done | Integrated | done |  | MRC
8258 | Basra | done | done | done | Integrated | 2025-10-25 |  | MFC
8868 | Thiqar | done | done | done | Integrated | done |  | KCT
7964 | Basra | 2026-02-13 | 2026-02-28 | 2026-02-27 | Integrated | 2025-10-26 |  | KCT
7793 | Thiqar | 2026-09-13 | 2026-09-06 | 2026-09-08 | Integrated | 2025-10-20 |  | KCT
7837 | Basra | done | done | done | Integrated | 2025-10-26 |  | MFC
8759 | Babil | 2025-10-24 | 2025-10-23 | 2025-10-24 | Integrated | 2025-11-01 |  | MRC
6374 | Basra | 2026-04-02 | 2026-04-09 | 2026-04-16 | Integrated | 2026-04-01 |  | TAC
6564 | Basra | 2026-04-01 | 2026-04-01 | 2026-04-01 | Integrated | 2026-04-01 |  | MRC
7969 | Thiqar | done | done | done | Integrated | done |  | KCT
8241 | Basra | done | done | done | Integrated | done |  | MFC
8256 | Basra | done | done | done | Integrated | done |  | MRC
6299 | Basra | 2026-05-01 | 2026-05-01 | 2026-05-01 | Integrated | 2026-05-01 |  | MRC
8804 | Basra | 2026-04-01 | 2026-04-01 | 2026-04-01 | Integrated | 2026-04-01 |  | MRC
8809 | Basra | 2026-05-01 | 2026-05-01 | 2026-05-01 | Integrated | 2026-05-01 |  | MFC
7706 | Missan | done | done | done | Integrated | done |  | MRC
8598 | Babil | done | 2025-11-30 | 2025-11-30 | Integrated | 2025-11-01 |  | TAC
8660 | Babil |  | 2025-11-03 | 2025-11-03 | Integrated | 2025-11-03 |  | MRC
6992 | Basra | done | done | done | Integrated | done |  | MFC
7226 | Basra | done | done | done | Integrated | done |  | KCT
8262 | Basra | done | done | done | Integrated | done |  | ATC
7968 | Thiqar | done | done | done | Integrated | done |  | KCT
7803 | Thiqar | done | done | done | Integrated | done |  | IPT
8259 | Basra | done | done | done | Integrated | done |  | Oraxel
8234 | Basra | done | done | done | Integrated | done |  | IPT
8242 | Basra | 2026-05-12 | 2026-05-12 | 2026-05-13 | Integrated | 2026-05-13 |  | ATC
8267 | Basra | done | done | done | Integrated | done |  | Shabakat
8805 | Basra | done | done | done | Integrated | done |  | Shabakat
8751 | Babil | 2025-11-26 | 2025-11-26 | 2025-11-26 | Integrated | 2025-11-28 |  | MFC
7458 | Thiqar | done | done | done | Integrated | done |  | IPT
7958 | Thiqar | 2025-12-01 | done | done | Integrated | done |  | IPT
8249 | Basra | done | done | done | Integrated | done |  | Shabakat
8268 | Basra | done | done | done | Integrated | done |  | ATC
6442 | Basra | 2026-05-01 | 2026-05-01 | 2026-05-01 | Integrated | 2026-05-01 |  | Metco
6562 | Basra | 2026-05-01 | 2026-05-01 | 2026-05-01 | Integrated | 2026-05-01 |  | Metco
7807 | Thiqar | done | done | done | Integrated | done |  | KCT
7889 | Basra | 2026-05-01 | 2026-05-01 | 2026-05-01 | Integrated | 2026-05-01 |  | MRC
7565 | Babil | 2025-12-02 | 2025-12-02 | 2025-12-03 | Integrated | 2025-12-04 |  | MFC
7562 | Babil | 2025-12-02 | 2025-12-02 | 2025-12-03 | Integrated | 2025-12-04 |  | MFC
7842 | Qaddissiya | 2025-12-06 | 2025-12-07 | 2025-12-08 | Integrated | 2025-12-09 |  | MRC
8239 | Basra | 2026-05-01 | 2026-05-01 | 2026-05-01 | Integrated | 2026-05-01 |  | ATC
7693 | Basra | 2026-05-01 | 2026-05-01 | 2026-05-01 | Integrated | 2026-05-01 |  | ATC
7836 | Basra | done | done | done | Integrated | done |  | MRC
8811 | Muthanna | 2025-12-09 | 2025-12-09 | 2025-12-12 | Integrated | 2025-12-13 |  | MFC
7266 | Muthanna | 2025-12-09 | 2025-12-09 | 2025-12-14 | Integrated | 2025-12-15 |  | MFC
7843 | Qaddissiya | 2025-12-09 | 2025-12-09 | 2025-12-12 | Integrated | 2025-12-13 |  | MRC
8734 | Babil | 2025-12-09 | 2025-12-09 | 2025-12-12 | Integrated | 2025-12-13 |  | MRC
7498 | Qaddissiya | 2025-12-12 | 2025-12-13 | 2025-12-14 | Integrated | 2025-12-28 |  | MFC
8253 | Basra | done | done | done | Integrated | done |  | Metco
6597 | Basra | done | done | done | Integrated | 2026-02-17 |  | Metco
7813 | Basra | done | done | done | Integrated | done |  | MRC
7592 | Thiqar | done | done | done | Integrated | done |  | KCT
8755 | Babil | 2025-12-24 | 2025-12-24 | 2025-12-26 | Integrated | 2025-12-26 |  | horizon
8733 | Babil | 2025-12-27 | 2025-12-27 | 2025-12-28 | Integrated | 2025-12-29 |  | horizon
8269 | Basra | 2026-04-01 | 2026-04-01 | 2026-04-01 | Integrated | 2026-04-01 |  | MFC
8245 | Basra | done | done | done | Integrated | 2026-02-04 |  | Metco
7756 | Basra | 2026-03-17 | 2026-03-17 | 2026-03-17 | Integrated | 2026-03-17 |  | Shabakat
7727 | Thiqar | done | done | done | Integrated | done |  | KCT
8238 | Basra | done | done | done | Integrated | done |  | ATC
7010 | Basra | done | done | done | Integrated | done |  | MFC
7785 | Missan | done | done | done | Integrated | 2026-02-13 |  | Metco
8292 | Missan | 2026-05-01 | 2026-05-01 | 2026-05-01 | Integrated | 2026-05-01 |  | Metco
8296 | Muthanna | 2026-01-23 | 2026-01-24 | 2026-01-27 | Integrated | 2026-01-27 |  | MRC
6514 | Basra | 2026-02-01 | 2026-02-01 | 2026-02-01 | Integrated | 2026-02-20 |  | KCT
8752 | Babil | 2026-01-04 | 2026-01-05 | 2026-01-06 | Integrated | 2026-01-16 |  | TAC
8162 | Qaddissiya | 2026-01-10 | 2026-01-11 | 2026-01-13 | Integrated | 2026-01-13 |  | MFC
8164 | Qaddissiya | 2026-01-10 | 2026-01-11 | 2026-01-13 | Integrated | 2026-01-13 |  | MRC
7802 | Thiqar | done | done | done | Integrated | done |  | KCT
7855 | Basra | done | done | 2026-01-12 | Integrated | done |  | Metco
7784 | Missan | 2026-12-12 | owner |  |  |  |  | MRC
8235 | Basra | 2026-01-12 | 2026-05-01 | 2026-01-12 | Integrated | 2026-05-01 |  | ATC
8683 | Basra | 2026-02-16 | 2026-02-16 | 2026-02-16 | Integrated | 2026-02-17 |  | Shabakat
7856 | Basra | 2026-05-01 | 2026-05-01 | 2026-05-01 | Integrated | 2026-01-21 |  | ATC
8350 | Missan | done | done | done | Integrated | 2026-01-20 |  | MRC
8366 | Missan | done | done | done | Integrated | 2026-01-22 |  | MRC
8304 | Missan | done | done | done | Integrated | 2026-01-20 |  | MRC
8305 | Missan | done | done | done | Integrated | 2026-01-20 |  | MRC
8328 | Missan | done | done | done | Integrated | 2026-01-21 |  | MRC
8178 | Missan | done | done | done | Integrated | 2026-01-20 |  | MRC
8311 | Missan | done | done | done | Integrated | 2026-01-22 |  | MRC
9716 | Thiqar | done | done | done | Integrated | 2026-01-22 |  | IPT
9718 | Thiqar | done | done | done | Integrated | 2026-01-23 |  | KCT
7974 | Thiqar | done | done | done | Integrated | 2026-01-22 |  | IPT
8603 | Muthanna | 2026-01-23 | 2026-01-24 | 2026-01-24 | Integrated | 2026-01-26 |  | MRC
8605 | Basra | 2026-05-01 | 2026-05-01 | 2026-05-01 | Integrated | 2026-02-14 |  | Metco
9721 | Thiqar | done | done | 2026-01-26 | Integrated | 2026-01-27 |  | KCT
9720 | Thiqar | done | done | 2026-01-26 | Integrated | 2026-01-27 |  | IPT
7862 | Basra |  |  | 2026-01-26 | Integrated | 2026-01-27 |  | ATC
7877 | Basra |  | done | 2026-01-26 | Integrated | 2026-01-27 | MIMO | IPT
7863 | Basra |  |  | 2026-01-28 | Integrated | 2026-01-28 |  | KCT
7868 | Basra | done | done | 2026-01-26 | Integrated | 2026-01-29 |  | MFC
7757 | Babil | 2026-01-27 | 2026-01-27 | 2026-01-28 | Integrated | 2026-01-28 | done | horizon
7864 | Basra | 0226-01-19 | 2026-01-19 | 2026-01-29 |  |  |  | MFC
9712 | Thiqar | done | done | done | Integrated | 2026-02-04 | MM | KCT
7867 | Basra | done | done | done | Integrated | 2026-02-13 |  | MFC
9714 | Thiqar | done | done | done | Integrated | 2026-02-11 |  | IPT
960 | Basra | done | done | done | Integrated | 2025-10-10 |  | IPT
8745 | Babil | 2025-12-29 | 2025-12-29 | 2025-12-30 | Integrated | 2025-12-31 |  | MRC
7766 | Babil | 2026-02-07 | 2026-02-08 | 2026-02-12 | Integrated | 2026-02-12 |  | MRC
7729 | Babil | 2026-02-09 | 2026-02-10 | 2026-02-11 | Integrated | 2026-02-11 | done | horizon
8158 | Qaddissiya | 2026-02-09 | 2026-02-10 | 2026-02-12 | Integrated | 2026-02-16 |  | MRC
8694 | Qaddissiya | 2026-02-09 | 2026-02-10 | 2026-02-12 | Integrated | 2026-02-16 |  | MRC
8168 | Qaddissiya | 2026-02-09 | 2026-02-10 | 2026-02-15 | Integrated | 2026-02-19 |  | MRC
8127 | Babil | 2026-02-18 | 2026-02-19 | 2026-02-19 | Integrated | 2026-02-23 |  | TAC
8813 | Babil | 2026-02-18 | 2026-02-19 | 2026-02-19 | Integrated | 2026-02-23 |  | horizon
7736 | Babil | 2026-02-18 | 2026-02-19 | 2026-02-20 | Integrated | 2026-03-01 |  | horizon
8337 | Missan | done | done | done | Integrated | 2026-02-10 |  | Metco
9710 | Thiqar | done | done | done | Integrated | done |  | KCT
9717 | Thiqar | done | done | done | Integrated | done |  | IPT
8306 | Missan | done | done | done | Integrated | 2026-02-28 |  | Metco
7869 | Basra | done | done | done | Integrated | 4-11 |  | Oraxel
7874 | Basra | done | done | done | Integrated | done | MM | IPT
8264 | Basra | 2026-05-01 | 2026-05-01 | 2026-05-01 | Integrated | 2026-05-01 |  | Shabakat
7871 | Basra | 2026-02-17 | done | done | Integrated | done |  | IPT
6520 | Basra | 2026-04-12 | 2026-04-12 | 2026-04-13 | Integrated | 2026-04-13 |  | Oraxel
8674 | Qaddissiya | 2026-02-17 | 2026-02-17 | 2026-02-18 | Integrated | 2026-02-19 |  | MRC
6441 | Muthanna | 2026-02-17 | 2026-02-17 | 2026-02-19 | Integrated | 2026-02-23 |  | MRC
8159 | Qaddissiya | 2026-02-19 | 2026-02-20 | 2026-02-21 | Integrated | 2026-02-25 |  | MRC
7259 | Muthanna | 2026-02-19 | 2026-02-19 | 2026-02-22 | Integrated | 2026-02-28 |  | MRC
7294 | Qaddissiya | 2026-02-19 | 2026-02-19 | 2026-02-21 | Integrated | 2026-02-25 |  | TAC
7787 | Muthanna | 2026-02-19 | 2026-02-19 | 2026-02-21 | Integrated | 2026-03-01 |  | MRC
8300 | Muthanna | 2026-02-19 | 2026-02-20 | 2026-02-20 | Integrated | 2026-03-01 |  | MRC
8696 | Qaddissiya | 2026-02-19 | 2026-02-19 | 2026-02-21 | Integrated | 2026-02-25 |  | TAC
8293 | Muthanna | 2026-02-25 | 2026-02-26 | 2026-02-26 | Integrated | 2026-02-28 |  | TAC
6518 | Basra | done | 2026-02-04 | 2026-02-05 | Integrated | 2026-02-06 |  | Oraxel
8177 | Missan | 2026-02-20 | 2026-02-21 | 2026-02-22 | Integrated | 2026-02-28 |  | Metco
8248 | Missan | 2026-02-23 | 2026-02-24 | 2026-02-24 | Integrated | 2026-02-28 |  | MRC
8294 | Muthanna | 2026-02-25 | 2026-02-26 | 2026-02-26 | Integrated | 2026-03-01 |  | MFC
7733 | Babil | 2026-02-24 | 2026-02-24 | 2026-02-25 | Integrated | 2026-02-27 |  | horizon
7866 | Basra | 2026-02-24 | 2026-02-25 | 2026-02-25 | Integrated | 2026-02-20 |  | MFC
7564 | Babil | 2026-03-08 | 2026-03-09 | 2026-03-10 | Integrated | 2026-03-14 |  | MRC
8298 | Muthanna | 2026-03-08 | 2026-03-09 | 2026-03-10 | Integrated | 2026-03-14 |  | MRC
8360 | Muthanna | 2026-03-08 | 2026-03-09 | 2026-03-10 | Integrated | 2026-03-14 |  | MRC
7735 | Babil | 2026-03-08 | 2026-03-09 | 2026-03-10 | Integrated | 2026-03-17 |  | MRC
9897 | Basra | 2026-03-14 | 2026-03-15 | 2026-03-16 | Integrated | 2026-03-17 |  | KCT
9908 | Basra | 2026-03-14 | 2026-03-15 | 2026-03-16 | Integrated | 2026-03-17 |  | MFC
9484 | Basra | 2026-03-14 | 2026-03-15 | 2026-03-16 | Integrated | 2026-03-17 |  | IPT
8744 | Babil | 2026-03-15 | 2026-03-16 | 2026-03-16 | Integrated | 2026-03-25 |  | KCT
8692 | Qaddissiya | 2026-03-15 | 2026-03-16 | 2026-03-17 | Integrated | 2026-03-29 |  | MRC
7719 | Babil | 2026-03-16 | 2026-03-16 | 2026-03-17 | Integrated | 2026-03-30 |  | TAC
7726 | Babil | 2026-03-16 | 2026-03-16 | 2026-03-17 | Integrated | 2026-03-30 |  | MRC
7878 | Basra | 2026-03-24 | 2026-03-25 | 2026-03-26 | Integrated | 2026-03-27 |  | KCT
9679 | Babil | 2026-03-28 | 2026-03-28 | 2026-03-28 | Integrated | 2026-04-01 |  | KCT
8746 | Babil | 2026-03-28 | 2026-03-28 | 2026-03-28 | Integrated | 2026-04-01 |  | TAC
9767 | Muthanna | 2026-03-28 | 2026-03-28 | 2026-03-28 | Integrated | 2026-05-01 |  | MRC
9883 | Basra | 2026-03-24 | 2026-03-25 | 2026-03-26 | Integrated | 2026-04-10 |  | Oraxel
9885 | Basra | 2026-03-24 | 2026-03-25 | 2026-03-26 | Integrated | 2026-04-10 |  | Oraxel
9899 | Basra | 2026-03-24 | 2026-03-25 | 2026-03-26 | Integrated | 2026-04-10 |  | Oraxel
8307 | Missan | 2026-08-04 | 2026-10-04 | 2026-10-04 | Integrated | 2026-04-14 |  | MRC
8865 | Thiqar | 2026-04-14 | 2026-04-14 | 2026-04-15 | Integrated | 2026-04-15 |  | KCT
7201 | Basra | 2026-04-14 | 2026-04-16 | 2026-04-19 | Integrated | 2026-04-19 |  | Oraxel
7203 | Basra | 2026-04-14 | 2026-04-14 | 2026-04-15 | Integrated | 2026-04-15 | Yes | Oraxel
8157 | Qaddissiya | 2026-04-16 | 2026-04-16 | 2026-04-17 | Integrated | 2026-04-20 |  | MFC
9886 | Basra | 2026-04-17 | 2026-04-19 | 2026-04-19 | Integrated | 2026-04-20 |  | MFC
6459 | Muthanna | 2026-04-16 | 2026-04-17 | 2026-04-17 | Integrated | 2026-04-22 |  | MRC
7261 | Muthanna | 2026-04-16 | 2026-04-17 | 2026-04-17 | Integrated | 2026-04-20 |  | MRC
8358 | Thiqar | 2026-04-26 | 2026-04-27 | 2026-04-27 | Integrated | 2026-04-28 |  | KCT
8867 | Thiqar | 2026-04-26 | 2026-04-27 | 2026-04-28 | Integrated | 2026-05-01 |  | IPT
6594 | Basra | 2026-04-01 | 2026-04-01 | 2026-04-01 | Integrated | 2026-04-01 |  | MRC
9711 | Thiqar | 2026-04-21 | 2026-04-21 | 2026-04-22 | Integrated | 2026-04-27 |  | KCT
8266 | Basra | 2026-01-20 | 2026-03-24 | 2026-02-12 | Integrated | 2026-04-23 |  | Shabakat
7213 | Basra | 2026-05-20 | 2026-05-21 | 2026-05-21 |  |  |  | Metco
8459 | Muthanna | 2026-04-27 | 2026-04-28 | 2026-04-28 | Integrated | 2026-04-29 |  | MRC
9888 | Basra | 2026-04-26 | 2026-04-27 | 2026-04-27 | Integrated | 2026-05-01 |  | IPT
9393 | Thiqar | 2026-05-12 | 2026-05-12 |  |  |  |  | KCT
9930 | Basra | 2026-04-30 | 2026-05-02 | 2026-05-02 | Integrated | 2026-05-12 |  | IPT
9902 | Basra | 2026-05-03 | 2026-05-06 | 2026-05-07 | Integrated | 2026-05-10 |  | Metco
9921 | Basra | 2026-05-03 | 2026-05-04 | 2026-05-05 | Integrated | 2026-05-11 |  | IPT
9922 | Basra | 2026-04-28 | 2026-04-29 | 2026-04-30 | Integrated | 2026-05-01 |  | MRC
9548 | Thiqar | 2026-04-30 | 2026-05-02 | 2026-05-02 | Integrated | 2026-05-12 |  | KCT
9542 | Thiqar | 2026-05-03 | 2026-05-05 | 2026-05-05 | Integrated | 2026-05-14 |  | KCT
9893 | Basra | 2026-05-03 | 2026-05-04 | 2026-05-05 | Integrated | 2026-05-10 |  | MRC
9917 | Basra | 2026-05-14 | 2026-05-14 | 2026-05-14 | Integrated | 2026-05-14 |  | KCT
9881 | Basra | 2026-05-03 | 2026-05-04 | 2026-05-05 | Integrated | 2026-05-10 |  | MRC
9895 | Basra | 2026-05-03 | 2026-05-04 | 2026-05-05 | Integrated | 2026-05-12 |  | Oraxel
7865 | Basra | 2026-05-10 | 2026-05-12 | 2026-05-12 | Integrated | 2026-05-14 |  | Metco
9676 | Qaddissiya | 2026-05-14 | 2026-05-14 | 2026-05-15 | Integrated | 2026-05-17 |  | MFC
9440 | Basra | 2026-05-14 | 2026-05-14 | 2026-05-16 | Reachable |  |  | KCT
9927 | Basra | 2026-05-14 | 2026-05-14 | 2026-05-16 | Reachable |  |  | KCT
9713 | Thiqar | 2026-05-17 | 2026-05-17 | 2026-05-22 |  |  |  | KCT
9880 | Basra | 2026-05-17 | 2026-05-17 | 2026-05-20 |  |  |  | KCT
9392 | Muthanna | 2026-05-17 | 2026-05-18 | 2026-05-19 | Integrated | 2026-05-20 |  | MRC
9682 | Qaddissiya | 2026-05-17 | 2026-05-18 | 2026-05-20 | Integrated | 2026-05-21 |  | MFC
9455 | Thiqar | 2026-05-18 | 2026-05-18 | 2026-05-22 |  |  |  | IPT
9564 | Thiqar | 2026-05-18 | 2026-05-18 | 2026-05-22 |  |  |  | IPT
9541 | Thiqar | 2026-05-18 | 2026-05-18 | 2026-05-20 |  |  |  | IPT
9928 | Basra | 2026-05-18 | 2026-05-18 | 2026-05-20 | Reachable |  |  | KCT
9892 | Basra | 2026-05-18 | 2026-05-18 | 2026-05-20 | Reachable |  |  | KCT